## Key dimensions
Key dimensions ¦ THẠCH BI
Nguồn: DWG lưu 23/10/2026. Đơn vị mm suy từ chuỗi kích thước và nhãn m; INSUNITS=1 (inch, đơn vị chèn). Chờ người thiết kế xác nhận; không tự đổi tỷ lệ.
Phiên bản 23102026 - Không dùng để thi công
ID | Part / witness | Parameter | Value (mm) | Value (m) | Drawing | Source | Basis | Axes | a1 (mm) | a2 (mm) | b1 (mm) | b2 (mm) | Limits / interpretation
DWG0001 | Overall ground-plan extent | Length | 67063.6 | 67.0636 | P05 | DIMENSION handle D7C2D8 | DRAWING SHOWN | X/Z | -13218.6 | -14822.8 | 53845 | -14822.8 | Plan witness X -13.2186 to +53.8450 m; differs from longitudinal section, ISSUE-C01.
DWG0385 | Overall longitudinal-section extent | Length | 67149.4 | 67.1494 | S45 | DIMENSION handle D7DBF5 | DRAWING SHOWN | X/Y | -13194.3 | -3493.7 | 53955.1 | -3493.7 | Section witness X -13.1943 to +53.9551 m; retain both extents, ISSUE-C01.
DWG0004 | Typical nave bay (axes 5-6) | Grid spacing | 4500 | 4.5 | P05 | DIMENSION handle D7C476 | DRAWING SHOWN | X/Z | 18975 | 15327.6 | 23475 | 15327.6 | 4.500 m typical bay; a grid distance, not a clear opening.
DWG0003 | Sanctuary bay (axes 9-10) | Grid spacing | 7200 | 7.2 | P05 | DIMENSION handle D7C47E | DRAWING SHOWN | X/Z | 36975 | 15184.9 | 44175 | 15327.6 | 7.200 m grid distance.
DWG0347 | Central transverse bay D-E | Grid spacing | 7200 | 7.2 | S25 | DIMENSION handle DA19A3 | DRAWING SHOWN | Z/Y | -3600 | -2800.8 | 3600 | -2800.8 | Z -3.600 to +3.600 m; not the clear width between column faces.
DWG0346 | Transverse bay C-D | Grid spacing | 3760 | 3.76 | S25 | DIMENSION handle DA19A2 | DRAWING SHOWN | Z/Y | -7360 | -2800.8 | -3600 | -2800.8 | Z -7.360 to -3.600 m.
DWG0345 | Transverse bay B-C | Grid spacing | 3054 | 3.054 | S25 | DIMENSION handle DA199F | DRAWING SHOWN | Z/Y | -10414 | -2800.8 | -7360 | -2800.8 | Z -10.414 to -7.360 m.
DWG0009 | Transverse bay H-I | Grid spacing | 2835 | 2.835 | P05 | DIMENSION handle D7C492 | DRAWING SHOWN | X/Z | -14997.6 | 13249 | -14997.6 | 10414 | Z +10.414 to +13.249 m.
DWG0311 | Nave section overall witness | Width | 22388 | 22.388 | S24 | DIMENSION handle D9E27C | DRAWING SHOWN | Z/Y | -11194 | -2080 | 11194 | -2080 | Z +/-11.194 m; a section envelope, distinct from the plan/facade widths.
DWG0196 | Twin-tower elevation overall witness | Width | 27254.2 | 27.2542 | E01B | DIMENSION handle C4566D | DRAWING SHOWN | Z/Y | 13627.1 | -3820.6 | -13627.2 | -3820.6 | 27.2542 m between the elevation witnesses; not the nave section width.
DWG0210 | Negative-Z tower base witness | Width | 4900 | 4.9 | E01B | DIMENSION handle C45673 | DRAWING SHOWN | Z/Y | -12603 | -2080 | -7703 | -2080 | 4.900 m dimension at courtyard level; confirm selected construction surfaces.
DWG0222 | Tower courtyard-to-cross top | Height | 39000 | 39 | E01B | DIMENSION handle C45681 | DRAWING SHOWN | Z/Y | -15358.7 | -2080 | -15358.7 | 36920 | 39.000 m = +36.920 minus courtyard -2.080 m.
DWG0223 | Nave floor above courtyard | Height | 2080 | 2.08 | E01B | DIMENSION handle C45677 | DRAWING SHOWN | Z/Y | -14753.6 | -2080 | -14552 | 0 | 2.080 m datum difference.
DWG0224 | First tower stage | Height | 8390 | 8.39 | E01B | DIMENSION handle C45678 | DRAWING SHOWN | Z/Y | -14552 | 0 | -14331.3 | 8390 | 0.000 to +8.390 m.
DWG0225 | Second tower-stage rise | Height | 7450 | 7.45 | E01B | DIMENSION handle C45679 | DRAWING SHOWN | Z/Y | -14331.3 | 8390 | -14191.3 | 15840 | +8.390 to +15.840 m.
DWG0195 | Central facade pier chain | Width | 5958.8 | 5.9588 | E01B | DIMENSION handle C45670 | DRAWING SHOWN | Z/Y | 2979.4 | -4522.4 | -2979.4 | -4522.4 | 5.9588 m between witnesses, flanked by 0.6206 m each side. Rounded labels need not close to 1 mm.
DWG0212 | Central door half-width witness | Half width | 2979.4 | 2.9794 | E01B | DIMENSION handle D7FF61 | DRAWING SHOWN | Z/Y | 2979.4 | 0 | 0 | 0 | 2.9794 m from centreline to witness; do not assume a door-leaf fabrication width.
DWG0228 | Central door vertical witness | Height | 4900 | 4.9 | E01B | DIMENSION handle C4567A | DRAWING SHOWN | Z/Y | -696.4 | 0 | -696.4 | 4900 | 4.900 m floor-to-head witness.
DWG0226 | Side door vertical witness | Height | 3756 | 3.756 | E01B | DIMENSION handle C4567D | DRAWING SHOWN | Z/Y | -5569.6 | 0 | -5569.6 | 3756 | 3.756 m floor-to-head witness.
DWG0312 | Nave timber-column section witness | Width | 594 | 0.594 | S24 | DIMENSION handle D9E253 | DRAWING SHOWN | Z/Y | -3897 | 3138.3 | -3303 | 3138.3 | 594 mm at the shown level; residual carved section and structural capacity unverified.
DWG0338 | Nave column-base rise | Height | 600 | 0.6 | S24 | DIMENSION handle D9E239 | DRAWING SHOWN | Z/Y | 3006.8 | 0 | 3325 | 600 | 600 mm floor-to-base witness.
DWG0339 | Nave timber-column vertical witness | Height | 8801.5 | 8.8015 | S24 | DIMENSION handle D9E242 | DRAWING SHOWN | Z/Y | 3020.3 | 600 | 3644.8 | 9401.5 | 8801.5 mm between the dimension endpoints, not an inferred bearing length.
DWG0342 | Nave courtyard-to-ridge drawn witness | Height | 14476.4 | 14.4764 | S24 | DIMENSION handle D9E021 | DRAWING SHOWN | Z/Y | 12485.4 | -2080 | 181.5 | 12396.4 | Ends at Y +12.3964 m; labels +12.472 m, ISSUE-R05 / RFI-S01.
DWG0383 | Sanctuary side cornice witness | Height | 6325 | 6.325 | S25 | DIMENSION handle DA1C4D | DRAWING SHOWN | Z/Y | 11306.8 | 0 | 11220.3 | 6325 | 6325 mm in section; elevations give 6324 mm, RFI-S02.
DWG0378 | Sanctuary platform rise | Height | 800 | 0.8 | S25 | DIMENSION handle DA1C41 | DRAWING SHOWN | Z/Y | 2567.6 | 0 | 2567.6 | 800 | 800 mm used by owner direction; ground-plan label still 750 mm, ISSUE-R04.
DWG0373 | Sanctuary side floor rise | Height | 160 | 0.16 | S25 | DIMENSION handle DA1C03 | DRAWING SHOWN | Z/Y | -4986.3 | 0 | -4990.4 | 160 | 160 mm used by owner direction; older PDF and plan label 150 mm.
DWG0380 | Sanctuary column base above dais | Height | 200 | 0.2 | S25 | DIMENSION handle DA1C4A | DRAWING SHOWN | Z/Y | 3321 | 1000 | 2879.8 | 800 | 200 mm, endpoints Y +0.800 to +1.000 m.
DWG0357 | Sanctuary central stepped element | Width | 1900 | 1.9 | S25 | DIMENSION handle DA1C44 | DRAWING SHOWN | Z/Y | -949 | 800 | 951 | 800 | 1900 mm at Y +0.800 m, Z -0.949 to +0.951 m. Steps, not a confirmed altar table.
DWG0372 | Sanctuary opening lower chain | Height | 2544.2 | 2.5442 | S25 | DIMENSION handle DA1C06 | DRAWING SHOWN | Z/Y | -4990.4 | 160 | -4878.4 | 2704.2 | 2544.2 mm between Y +0.160 and +2.7042 m; ISSUE-R03.
DWG0376 | Sanctuary opening intermediate chain | Height | 466.3 | 0.4663 | S25 | DIMENSION handle DA1C09 | DRAWING SHOWN | Z/Y | -4878.4 | 2704.2 | -4886.8 | 3170.5 | 466.3 mm between Y +2.7042 and +3.1705 m; ISSUE-R03.
DWG0375 | Sanctuary opening upper chain | Height | 4392.2 | 4.3922 | S25 | DIMENSION handle DA1C0C | DRAWING SHOWN | Z/Y | -4886.8 | 3170.5 | -5462 | 7562.7 | 4392.2 mm between Y +3.1705 and +7.5627 m; ISSUE-R03.
DWG0377 | Sanctuary inner vertical witness A | Height | 6231 | 6.231 | S25 | DIMENSION handle DA1C0F | DRAWING SHOWN | Z/Y | -2911.2 | 3170.5 | -3600 | 9401.5 | 6231 mm; older PDF 6301 mm, ISSUE-R03.
DWG0379 | Sanctuary inner vertical witness B | Height | 8524.6 | 8.5246 | S25 | DIMENSION handle DA1C47 | DRAWING SHOWN | Z/Y | 3303 | 9524.5 | 3321 | 1000 | 8524.6 mm, approximately 8525; older PDF 8452 mm, ISSUE-R03.
DWG0381 | Sanctuary side opening reference | Height | 3170.5 | 3.1705 | S25 | DIMENSION handle DA1C32 | DRAWING SHOWN | Z/Y | 6379.1 | 0 | 6379.1 | 3170.5 | 3170.5 mm rounded measurement; retain source precision and CAD label, ISSUE-R03.
DWG0240 | Window-bay elevation module | Grid spacing | 4500 | 4.5 | E26 | DIMENSION handle DA3D32 | DRAWING SHOWN | u/v | 1614.5 | 1597.3 | 6114.5 | 1597.3 | 4500 mm. Local u/v endpoints are not global XYZ.
DWG0251 | Window-bay lower opening witness | Height | 2100.5 | 2.1005 | E26 | DIMENSION handle DA3D38 | DRAWING SHOWN | u/v | 2864.5 | 3079.2 | 2864.5 | 5179.7 | 2100.5 mm between dimension endpoints; not a complete window fabrication schedule.
DWG0562 | Window detail outer vertical witness | Height | 2440.5 | 2.4405 | D29 | DIMENSION handle DAD681 | DRAWING SHOWN | u/v | 2854.6 | 3046.5 | 2763.9 | 5487 | 2440.5 mm in D29; verify the shown edges before procurement.
DWG0281 | Doorway-bay outer opening witness | Width | 2250 | 2.25 | E31 | DIMENSION handle DA2E91 | DRAWING SHOWN | u/v | 2739.8 | 2434.2 | 4989.8 | 2434.2 | 2250 mm in E31; distinct from the 1845 mm inner witness.
DWG0279 | Doorway-bay inner opening witness | Width | 1845 | 1.845 | E31 | DIMENSION handle DA30D4 | DRAWING SHOWN | u/v | 9078.2 | 2229.1 | 10923.2 | 2229.1 | 1845 mm in E31; verify finishes and leaves separately.
DWG0288 | Doorway-bay vertical witness | Height | 2950.5 | 2.9505 | E31 | DIMENSION handle DA309D | DRAWING SHOWN | u/v | 4301.2 | 2229.1 | 4989.8 | 5179.6 | 2950.5 mm in E31.
DWG0597 | Door detail outer opening witness | Width | 2250 | 2.25 | D34 | DIMENSION handle DAD767 | DRAWING SHOWN | u/v | 2224.5 | 2088.9 | 4474.5 | 1973.1 | 2250 mm in D34; local axes only.
DWG0636 | Door detail overall vertical witness | Height | 3100.5 | 3.1005 | D34 | DIMENSION handle DAD75B | DRAWING SHOWN | u/v | 3349.5 | 4607 | 3349.5 | 1506.5 | 3100.5 mm between the shown edges.
DWG0686 | Steel arch-frame grid span | Grid spacing | 7200 | 7.2 | D46 | DIMENSION handle DA5CD6 | DRAWING SHOWN | u/v | 3194.6 | 1034.3 | 10394.6 | 1034.3 | 7200 mm in D46; load path, steel sections and connections remain ENGINEERING HOLD.
DWG0691 | Steel arch-frame inner span witness | Width | 6606 | 6.606 | D46 | DIMENSION handle DA5CCD | DRAWING SHOWN | u/v | 3491.6 | 2527 | 10097.6 | 2519 | 6606 mm; local u/v endpoints only.
DWG0682 | Steel arch inclined outer witness | Inclined length | 4278.2 | 4.2782 | D46 | DIMENSION handle DA5C91 | DRAWING SHOWN | u/v | 3254.6 | 8729.6 | 6794.6 | 11131.9 | 4278.2 mm; no member capacity inferred.
DWG0715 | Concrete arch-frame grid span | Grid spacing | 7200 | 7.2 | D47 | DIMENSION handle DA5CE2 | DRAWING SHOWN | u/v | 3194.6 | 947.5 | 10394.6 | 947.5 | 7200 mm in D47; reinforcement and connection design remain ENGINEERING HOLD.
DWG0717 | Concrete arch-frame inner span witness | Width | 6606 | 6.606 | D47 | DIMENSION handle DA5CDC | DRAWING SHOWN | u/v | 3491.6 | 2580 | 10097.6 | 3105 | 6606 mm; local u/v endpoints only.
DWG0712 | Concrete arch inclined outer witness | Inclined length | 4779.5 | 4.7795 | D47 | DIMENSION handle DA5D00 | DRAWING SHOWN | u/v | 2839.7 | 8871.1 | 6794.6 | 11554.9 | 4779.5 mm; no member capacity inferred.
F01 | Ground-storey cornice top over the side bays | Y level | 8390 | 8.39 | E01B | facade.csv F01 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/Y |  |  |  |  | 8.390; Kept from the bundle's traced facade; also the +8.390 level label
F04 | Upper-storey plinth top (terrace) | Y level | 9741 | 9.741 | E01B | facade.csv F04 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/Y |  |  |  |  | 9.741; Floor of the side niches and of the room behind the triple window
F06 | Upper entablature top | Y level | 15840 | 15.84 | E01B | facade.csv F06 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/Y |  |  |  |  | 15.840; Also the +15.840 level label and plan PT15
F08 | Central great arch extrados | Radius | 2270 | 2.27 | E01B | facade.csv F08 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/Y |  |  |  |  | r 2.270 about +12.677; Rings at r 2.070 and 2.200 drawn between; arc centre (0, 12677) mm, radius 2270 mm
F09 | Central great arch intrados | Radius | 1960 | 1.96 | E01B | facade.csv F09 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/Y |  |  |  |  | r 1.960; Tympanum face inside it; arc centre (0, 12677) mm, radius 1960 mm
F10 | Triple window outer lights | Radius | 430 | 0.43 | E01B | facade.csv F10 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/Y |  |  |  |  | centres ±1.190, r 0.430 about +12.241; Glazing r 0.375; rings to r 0.650; arc centre (-1190, 12241) mm, radius 430 mm
F12 | Triple window glazing edge and sill | Y level | 9984 | 9.984 | E01B | facade.csv F12 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/Y |  |  |  |  | sill +9.984; Lights 0.830 m wide between colonnettes
F15 | Side niche (intrados) | Radius | 599 | 0.599 | E01B | facade.csv F15 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/Y |  |  |  |  | r 0.599 about +12.308; crown +12.907; pedestal top +10.391 m; statue placement is CONCEPT; arc centre (-5350, 12308) mm, radius 599 mm
F17 | Central niche (intrados) | Radius | 711 | 0.711 | E01B | facade.csv F17 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/Y |  |  |  |  | r 0.711 about +18.893; crown +19.604; Pedestal 15.997–16.683; arc centre (0, 18893) mm, radius 711 mm
F18 | Central aedicule arch extrados | Radius | 1112 | 1.112 | E01B | facade.csv F18 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/Y |  |  |  |  | r 1.112; arc centre (0, 18893) mm, radius 1112 mm
F22 | Cross top | Y level | 24648 | 24.648 | E01B | facade.csv F22 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/Y |  |  |  |  | 24.648; Highest point of the central facade
F23 | Central pier front at the plinth | X position | 1562 | 1.562 | PT10 | facade.csv F23 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/X |  |  |  |  | X 1.562; Plan at +10.128 m; X from axis 1
F24 | Central bay wall face | X position | 2936 | 2.936 | PT10 | facade.csv F24 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/X |  |  |  |  | X 2.936
F25 | Triple window plane | X position | 3556 | 3.556 | PT10 | facade.csv F25 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/X |  |  |  |  | X 3.556 (louvres); Room behind from X 3.666 to 4.716
F26 | Side bay wall face | X position | 4017 | 4.017 | PT10 | facade.csv F26 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/X |  |  |  |  | X 4.017
F27 | Side bay wall back | X position | 4936 | 4.936 | PT10 | facade.csv F27 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/X |  |  |  |  | X 4.936
F28 | Pinnacle pedestal front | X position | 2096 | 2.096 | PT15 | facade.csv F28 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/X |  |  |  |  | X 2.096; Plan at +15.840 m
F29 | Aedicule pier front | X position | 3805 | 3.805 | PT15 | facade.csv F29 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/X |  |  |  |  | X 3.805
F30 | Central niche column front | X position | 3915 | 3.915 | PT15 | facade.csv F30 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/X |  |  |  |  | X 3.915
F31 | Central niche (plan) | Radius | 711 | 0.711 | PT15 | facade.csv F31 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/X |  |  |  |  | centre X 4.225, r 0.711; Niche back X 4.936; aedicule back X 5.046; arc centre (0, 4225) mm, radius 711 mm
F32 | Cresting balustrade front | X position | 3376 | 3.376 | PT15 | facade.csv F32 (geometry checked within 1.5 mm) | DERIVED / TRACED | Z/X |  |  |  |  | X 3.376; Fleur-de-lis posts at 617 mm spacing
LEVEL-E01B--2080 | Courtyard datum | Y level | -2080 | -2.08 | E01B | levels.csv E01B: - 2,08M | DRAWING SHOWN | Y |  |  |  |  | Label - 2,08M; marker -2080.0 mm; matches.
LEVEL-E01B-0 | Nave floor datum | Y level | 0 | 0 | E01B | levels.csv E01B: +00M | DRAWING SHOWN | Y |  |  |  |  | Label +00M; marker 0.0 mm; matches.
LEVEL-E01B-8390 | Tower lower-stage level | Y level | 8390 | 8.39 | E01B | levels.csv E01B: + 8,390M | DRAWING SHOWN | Y |  |  |  |  | Label + 8,390M; marker 8390.0 mm; matches.
LEVEL-E01B-15840 | Tower upper-stage level | Y level | 15840 | 15.84 | E01B | levels.csv E01B: + 15,840M | DRAWING SHOWN | Y |  |  |  |  | Label + 15,840M; marker 15840.0 mm; matches.
LEVEL-E01B-23140 | Tower intermediate level | Y level | 23140 | 23.14 | E01B | levels.csv E01B: + 23,140M | DRAWING SHOWN | Y |  |  |  |  | Label + 23,140M; marker 23140.0 mm; matches.
LEVEL-E01B-29090 | Tower cap base level | Y level | 29090 | 29.09 | E01B | levels.csv E01B: + 29,09M | DRAWING SHOWN | Y |  |  |  |  | Label + 29,09M; marker 29090.0 mm; matches.
LEVEL-E01B-36920 | Tower cross top above nave floor | Y level | 36920 | 36.92 | E01B | levels.csv E01B: + 36,920M | DRAWING SHOWN | Y |  |  |  |  | Label + 36,920M; marker 36920.0 mm; matches.
LEVEL-EW-6324 | Wing cornice label | Y level | 6324 | 6.324 | EW | levels.csv EW: + 6,324M | DRAWING SHOWN | Y |  |  |  |  | Label + 6,324M; marker 6323.9 mm; matches. Section 6325 mm differs by 1 mm; RFI-S02.
LEVEL-EW-9830 | Wing roof reference label | Y level | 9830 | 9.83 | EW | levels.csv EW: + 9,830M | DRAWING SHOWN | Y |  |  |  |  | Label + 9,830M; marker 9829.6 mm; matches. Exact roof surface remains to be confirmed, ISSUE-C02.
LEVEL-EW-15187 | Wing cross-top label | Y level | 15187 | 15.187 | EW | levels.csv EW: + 15,187M | DRAWING SHOWN | Y |  |  |  |  | Label + 15,187M; marker 15186.9 mm; matches.

## Grid positions
Grid positions ¦ THẠCH BI
Source: DWG saved 2026-10-23, source file 10; SHA-256 in sheets.json. Millimetres inferred; owner-selected project basis 2026-10-26.
In development / Đang phát triển - Not for construction / Không dùng để thi công
Axis | Grid | Coordinate (mm) | Coordinate (m) | Source IDs | Register cell | Meaning / limits
X | 1 | 0 | 0 | P128 | Model grid!D8 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
X | 2 | 4900 | 4.9 | P001, P129 | Model grid!D9 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
X | 2′ | 5475 | 5.475 | P002, P130 | Model grid!D10 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
X | 3 | 9975 | 9.975 | P003, P131 | Model grid!D11 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
X | 4 | 14475 | 14.475 | P004, P132 | Model grid!D12 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
X | 5 | 18975 | 18.975 | P005, P133 | Model grid!D13 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
X | 6 | 23475 | 23.475 | P006, P134 | Model grid!D14 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
X | 7 | 27975 | 27.975 | P007, P135 | Model grid!D15 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
X | 8 | 32475 | 32.475 | P008, P136 | Model grid!D16 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
X | 9 | 36975 | 36.975 | P009, P137 | Model grid!D17 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
X | 10 | 44175 | 44.175 | P010, P138 | Model grid!D18 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
X | 11 | 48675 | 48.675 | P011, P139 | Model grid!D19 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
X | 12 | 53016 | 53.016 | P012, P140 | Model grid!D20 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
Z | A | -13249 | -13.249 | P141, P154 | Model grid!D28 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
Z | B | -10414 | -10.414 | P013, P142, P154 | Model grid!D29 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
Z | C | -7360 | -7.36 | P014, P143, P154 | Model grid!D30 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
Z | D | -3600 | -3.6 | P015, P144, P154 | Model grid!D31 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
Z | E | 3600 | 3.6 | P016, P145, P154 | Model grid!D32 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
Z | G | 7360 | 7.36 | P017, P146, P154 | Model grid!D33 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
Z | H | 10414 | 10.414 | P018, P147, P154 | Model grid!D34 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.
Z | I | 13249 | 13.249 | P019, P148, P154 | Model grid!D35 | DWG grid-check.csv agrees within 0.1 mm; grid centreline, not finished face.

## Drawing index
Drawing index ¦ THẠCH BI
Source: DWG saved 2026-10-23, source file 10; SHA-256 in sheets.json. Millimetres inferred; owner-selected project basis 2026-10-26.
In development / Đang phát triển - Not for construction / Không dùng để thi công
ID | DWG sheet | Drawing / view | Axes | Dimension objects | Full PDF | Zoom views
P05 | 5 | Ground-floor plan +0.00 | X/Z | 22 | views/P05_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
P14 | 14 | Plan at +6.324 m (body) and +8.390 m (tower end) | X/Z | 16 | views/P14_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
PT08 | unnumbered | Tower plan at +8.390 m (first tower stage) | u/v | 4 | views/PT08_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
PT10 | unnumbered | Tower-end plan at +10.128 m | u/v | 0 | views/PT10_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
PT15 | unnumbered | Tower-end plan at +15.840 m | u/v | 0 | views/PT15_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
PT15A | unnumbered | Single-tower plan at +15.84 m | u/v | 2 | views/PT15A_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
PT23 | unnumbered | Single-tower plan at +23.14 m | u/v | 0 | views/PT23_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
PT29 | unnumbered | Single-tower plan at +29.09 m | u/v | 0 | views/PT29_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
P28 | 28 | Plan of one window bay | u/v | 74 | views/P28_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
P33 | 33 | Plan of one doorway bay, axes 4–5 (no title) | u/v | 53 | views/P33_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
E01A | 1 | Twin-tower end elevation, variant A (cut through the nave roof) | Z/Y | 23 | views/E01A_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
E01B | 1 | Twin-tower end elevation, variant B (full elevation) | Z/Y | 36 | views/E01B_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
E02 | unnumbered | Side elevation (no title) | X/Y | 0 | views/E02_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
E03 | 3 | Gabled-end elevation | Z/Y | 9 | views/E03_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
EW | unnumbered | Side-wing end elevations, outside and inside | u/v | 0 | views/EW_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
ET | unnumbered | Single tower elevation (no frame or title) | u/v | 0 | views/ET_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
E26 | 26 | Window-bay wall elevations, outside and inside | u/v | 35 | views/E26_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
E31 | 31 | Doorway-bay wall elevations, outside and inside | u/v | 30 | views/E31_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
S24 | 24 | Nave transverse section | Z/Y | 38 | views/S24_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
S25 | 25 | Sanctuary transverse section | Z/Y | 42 | views/S25_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
S45 | 45 | Longitudinal section A-A | X/Y | 24 | views/S45_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
S27 | 27 | Window-bay section A-A | u/v | 64 | views/S27_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
S32 | 32 | Doorway-bay section A-A | u/v | 57 | views/S32_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
D29 | 29 | Window detail without leaves, both sides (no frame) | u/v | 62 | views/D29_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
D34 | 34 | Doorway detail without leaves, both sides (no frame) | u/v | 90 | views/D34_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
D46 | 46 | Steel arch-frame elevation, side wings on axes C and G | u/v | 30 | views/D46_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json
D47 | 47 | Reinforced-concrete arch frame, side wings on axes C and G | u/v | 15 | views/D47_full.pdf | See 02_Enlarged_Details.pdf and export-manifest.json