## Read me
Sound: equipment and electrical register
Purpose | Manage equipment specifications, locations, stable IDs, control mapping and electrical-line specifications against one shared layout.
Baseline | Sound. Loudspeakers, microphones, indoor speech and outdoor overflow. Model snapshot: 2026-10-09T00:46:12.718Z.
Current equipment | 30
Current routes | 40
Retired equipment / routes | 4
Coordinates | Metres: X toward sanctuary from axis 1; Y up from nave ±0.000; negative Z toward B, positive toward H.
Amber columns | Editable engineering inputs. Approved products/specifications, control IDs, notes and cable allowances survive refresh by ID. Blank means pending.
Model columns | Imported positions, IDs, planning specs and route vertices refresh from paired layout/systems exports. Use Proposed X/Y/Z for position revisions.
Position changes | Enter all three Proposed coordinates; export a draft layout, import it in the viewer, check supports/aim/clearances, then export matching layout and systems JSON. Enclosures require a coordinated model-source change.
Line lengths | Route length sums the ordered 3D segments. Full home-run length adds its upstream path once. Do not add shared bundles again; no procurement total is implied.
Specifications | Catalogue values and procedural dimensions are planning proxies. Final cable type, core count, cross-section, containment and approvals remain blank until designed.
Source layout SHA-256 | 4ae7e1535959a20d2f5749b1ba03c885f39cbcfde41c0856c11d90946754f1c6
Source systems SHA-256 | e2130aeffb518d934149fa35c32d858856db06e804d9cb98aac4f1896cd3b761
Layout version | 2026-10-16-tower-board; sanctuary 2026-10-07-sanctuary-8
Layout source | docs/electrical-grid/equipment-layout.json
Systems source | docs/electrical-grid/electrical-systems.json
Viewer | Thach_Bi_Viewer/OPEN_CHURCH.html → Simulator → Wiring. Equipment IDs and route IDs match both the 2D and 3D views.
Refresh | See docs/electrical-grid/register.md. Edit amber fields in the usage-category files. Refresh preserves their values by ID, retains retired records and updates the summary report.
Known limits | Physical switching channels and cable specifications are pending. Current feedback, speech clarity and other design shortfalls remain open.
Scope | Loudspeakers, microphones, indoor speech and outdoor overflow. Shared board sources are cross-references to the distribution-controls register; they are not duplicated here. Architectural fabric stays in the drawing specifications.
Release status | Design development; not issued for purchasing, installation or construction.

## Equipment
Sound: equipment
Model fields refresh from matching layout exports. Amber columns are retained engineering inputs.
Current X/Y/Z use metres, Y up from nave datum. Use all three Proposed coordinates to prepare a layout revision.
Filter by ID, board, circuit or status. Retired rows retain prior engineering inputs.
Equipment ID | Name | Category | Board | Circuit | X (m) | Y (m) | Z (m) | Mount | Visibility | Command state | Model envelope (mm) | Planning specs | Rated estimate (W) | Yaw (deg) | Tilt (deg) | Manufacturer | Product model | Approved specs | Datasheet / approval | Manual control ID | Control group | Proposed X (m) | Proposed Y (m) | Proposed Z (m) | Engineering notes | Record state | Route IDs | Model parameters
S261 | Wall speaker · axis 4 · B | speaker | DB1 | A1 | 14.475 | 3.45 | -7.07 | wall | Shown | On | 146 × 600 × 60 | 60 W audio rating · Passive / amplifier output · 85.1 ms delay. Passive speaker; audio rating is not mains demand | 20 | 140 | -18 | [10 empty] | Current | drop:AV1:A1:audio:-1:S261 | {"dim":1,"level":-6,"delayMs":85.1}
S262 | Wall speaker · axis 4 · H | speaker | DB1 | A1 | 14.475 | 3.45 | 7.07 | wall | Shown | On | 146 × 600 × 60 | 60 W audio rating · Passive / amplifier output · 86.2 ms delay. Passive speaker; audio rating is not mains demand | 20 | -140 | -18 | [10 empty] | Current | drop:AV1:A1:audio:1:S262 | {"dim":1,"level":-6,"delayMs":86.2}
S263 | Wall speaker · axis 5 · B | speaker | DB1 | A1 | 18.975 | 3.45 | -7.07 | wall | Shown | On | 146 × 600 × 60 | 60 W audio rating · Passive / amplifier output · 72.2 ms delay. Passive speaker; audio rating is not mains demand | 20 | 140 | -18 | [10 empty] | Current | drop:AV1:A1:audio:-1:S263 | {"dim":1,"level":-6,"delayMs":72.2}
S264 | Wall speaker · axis 5 · H | speaker | DB1 | A1 | 18.975 | 3.45 | 7.07 | wall | Shown | On | 146 × 600 × 60 | 60 W audio rating · Passive / amplifier output · 73.5 ms delay. Passive speaker; audio rating is not mains demand | 20 | -140 | -18 | [10 empty] | Current | drop:AV1:A1:audio:1:S264 | {"dim":1,"level":-6,"delayMs":73.5}
S265 | Wall speaker · axis 6 · B | speaker | DB1 | A1 | 23.475 | 3.45 | -7.07 | wall | Shown | On | 146 × 600 × 60 | 60 W audio rating · Passive / amplifier output · 59.2 ms delay. Passive speaker; audio rating is not mains demand | 20 | 140 | -18 | [10 empty] | Current | drop:AV1:A1:audio:-1:S265 | {"dim":1,"level":-6,"delayMs":59.2}
S266 | Wall speaker · axis 6 · H | speaker | DB1 | A1 | 23.475 | 3.45 | 7.07 | wall | Shown | On | 146 × 600 × 60 | 60 W audio rating · Passive / amplifier output · 60.8 ms delay. Passive speaker; audio rating is not mains demand | 20 | -140 | -18 | [10 empty] | Current | drop:AV1:A1:audio:1:S266 | {"dim":1,"level":-6,"delayMs":60.8}
S267 | Wall speaker · axis 7 · B | speaker | DB1 | A1 | 27.975 | 3.45 | -7.07 | wall | Shown | On | 146 × 600 × 60 | 60 W audio rating · Passive / amplifier output · 46.3 ms delay. Passive speaker; audio rating is not mains demand | 20 | 140 | -18 | [10 empty] | Current | drop:AV1:A1:audio:-1:S267 | {"dim":1,"level":-6,"delayMs":46.3}
S268 | Wall speaker · axis 7 · H | speaker | DB1 | A1 | 27.975 | 3.45 | 7.07 | wall | Shown | On | 146 × 600 × 60 | 60 W audio rating · Passive / amplifier output · 48.3 ms delay. Passive speaker; audio rating is not mains demand | 20 | -140 | -18 | [10 empty] | Current | drop:AV1:A1:audio:1:S268 | {"dim":1,"level":-6,"delayMs":48.3}
S269 | Wall speaker · axis 8 · B | speaker | DB1 | A1 | 32.475 | 3.45 | -7.07 | wall | Shown | On | 146 × 600 × 60 | 60 W audio rating · Passive / amplifier output · 33.5 ms delay. Passive speaker; audio rating is not mains demand | 20 | 140 | -18 | [10 empty] | Current | drop:AV1:A1:audio:-1:S269 | {"dim":1,"level":-6,"delayMs":33.5}
S270 | Wall speaker · axis 8 · H | speaker | DB1 | A1 | 32.475 | 3.45 | 7.07 | wall | Shown | On | 146 × 600 × 60 | 60 W audio rating · Passive / amplifier output · 36 ms delay. Passive speaker; audio rating is not mains demand | 20 | -140 | -18 | [10 empty] | Current | drop:AV1:A1:audio:1:S270 | {"dim":1,"level":-6,"delayMs":36}
S271 | Wall speaker · axis 9 · B | speaker | DB1 | A1 | 36.975 | 3.45 | -7.07 | wall | Shown | On | 146 × 600 × 60 | 60 W audio rating · Passive / amplifier output · 20.6 ms delay. Passive speaker; audio rating is not mains demand | 20 | 140 | -18 | [10 empty] | Current | drop:AV1:A1:audio:-1:S271 | {"dim":1,"level":-6,"delayMs":20.6}
S272 | Wall speaker · axis 9 · H | speaker | DB1 | A1 | 36.975 | 3.45 | 7.07 | wall | Shown | On | 146 × 600 × 60 | 60 W audio rating · Passive / amplifier output · 24.1 ms delay. Passive speaker; audio rating is not mains demand | 20 | -140 | -18 | [10 empty] | Current | drop:AV1:A1:audio:1:S272 | {"dim":1,"level":-6,"delayMs":24.1}
S273 | Wall speaker · entrance hall · B | speaker | DB1 | A5 | 2.655 | 3.6 | -3.05 | wall | Shown | Off | 146 × 600 × 60 | 60 W audio rating · Passive / amplifier output · 94.9 ms delay. Passive speaker; audio rating is not mains demand | 20 | -6.4764 | -26.2062 | [10 empty] | Current | drop:AV1:A5:audio:-1:S273 | {"dim":1,"level":-9,"delayMs":94.9}
S274 | Wall speaker · entrance hall · H | speaker | DB1 | A5 | 2.655 | 3.6 | 3.05 | wall | Shown | Off | 146 × 600 × 60 | 60 W audio rating · Passive / amplifier output · 96.5 ms delay. Passive speaker; audio rating is not mains demand | 20 | 6.4764 | -26.2062 | [10 empty] | Current | drop:AV1:A5:audio:1:S274 | {"dim":1,"level":-9,"delayMs":96.5}
S276 | Wing speaker · B · toward entrance · held | speaker | DB1 | A1 | 43.72 | 4.85 | -13.06 | wall | Shown | On | 146 × 600 × 60 | 60 W audio rating · Passive / amplifier output · 22.9 ms delay. Passive speaker; audio rating is not mains demand | 20 | 180 | -50 | [10 empty] | Current | drop:AV1:A1:audio:-1:S276 | {"dim":1,"level":-6,"delayMs":22.9,"anchorY":4.85,"note":"ENGINEERING HOLD: two total wall speakers toward entrance (-X), raised for full fan/return-wall envelope clearance. Speech and feedback still require coordinated validation; product, concealment, fixi"}
S278 | Wing speaker · H · toward entrance · held | speaker | DB1 | A1 | 43.72 | 4.85 | 13.06 | wall | Shown | On | 146 × 600 × 60 | 60 W audio rating · Passive / amplifier output · 37.1 ms delay. Passive speaker; audio rating is not mains demand | 20 | 180 | -50 | [10 empty] | Current | drop:AV1:A1:audio:1:S278 | {"dim":1,"level":-6,"delayMs":37.1,"anchorY":4.85,"note":"ENGINEERING HOLD: two total wall speakers toward entrance (-X), raised for full fan/return-wall envelope clearance. Speech and feedback still require coordinated validation; product, concealment, fixi"}
S279 | Veranda fill · B · 12.2 | speaker | DB1 | A2 | 12.225 | 3.9 | -8.85 | pendant | Shown | On | 367 × 257 × 260 | 30 W audio rating · Passive / amplifier output · 88.8 ms delay. Passive speaker; audio rating is not mains demand | 10 | 0 | -90 | [10 empty] | Current | drop:AV1:A2:audio:-1:S279 | {"dim":1,"level":-7,"delayMs":88.8,"anchorY":6.798875000000001}
S280 | Veranda fill · B · 25.7 | speaker | DB1 | A2 | 25.725 | 3.9 | -8.85 | pendant | Shown | On | 367 × 257 × 260 | 30 W audio rating · Passive / amplifier output · 50.9 ms delay. Passive speaker; audio rating is not mains demand | 10 | 0 | -90 | [10 empty] | Current | drop:AV1:A2:audio:-1:S280 | {"dim":1,"level":-7,"delayMs":50.9,"anchorY":6.798875000000001}
S281 | Veranda fill · H · 12.2 | speaker | DB1 | A2 | 12.225 | 3.9 | 8.85 | pendant | Shown | On | 367 × 257 × 260 | 30 W audio rating · Passive / amplifier output · 92.3 ms delay. Passive speaker; audio rating is not mains demand | 10 | 0 | -90 | [10 empty] | Current | drop:AV1:A2:audio:1:S281 | {"dim":1,"level":-7,"delayMs":92.3,"anchorY":6.798875000000001}
S282 | Veranda fill · H · 25.7 | speaker | DB1 | A2 | 25.725 | 3.9 | 8.85 | pendant | Shown | On | 367 × 257 × 260 | 30 W audio rating · Passive / amplifier output · 56.8 ms delay. Passive speaker; audio rating is not mains demand | 10 | 0 | -90 | [10 empty] | Current | drop:AV1:A2:audio:1:S282 | {"dim":1,"level":-7,"delayMs":56.8,"anchorY":6.798875000000001}
S283 | Courtyard horn · B | speaker | DB1 | A3 | -0.14 | 6.2 | -8.3 | wall | Shown | Off | 420 × 400 × 400 | 30 W audio rating · Passive / amplifier output · 99.4 ms delay. Passive speaker; audio rating is not mains demand | 10 | 172.1256 | -14.4345 | [10 empty] | Current | drop:AV1:A3:audio:-1:S283 | {"dim":1,"level":-4,"delayMs":99.4}
S284 | Tower horn · B · outer | speaker | DB1 | A3 | -0.14 | 6.2 | -11.9 | wall | Shown | Off | 420 × 400 × 400 | 30 W audio rating · Passive / amplifier output · 91.3 ms delay. Passive speaker; audio rating is not mains demand | 10 | -172.5973 | -14.4498 | [10 empty] | Current | drop:AV1:A3:audio:-1:S284 | {"dim":1,"level":-4,"delayMs":91.3}
S285 | Side courtyard horn · axis 5 · B | speaker | DB1 | A3 | 18.975 | 5.6 | -10.75 | wall | Shown | Off | 420 × 400 × 400 | 30 W audio rating · Passive / amplifier output · 62 ms delay. Passive speaker; audio rating is not mains demand | 10 | -90 | -26.4631 | [10 empty] | Current | drop:AV1:A3:audio:-1:S285 | {"dim":1,"level":-6,"delayMs":62}
S286 | Side courtyard horn · axis 8 · B | speaker | DB1 | A3 | 32.475 | 5.6 | -10.75 | wall | Shown | Off | 420 × 400 × 400 | 30 W audio rating · Passive / amplifier output · 25 ms delay. Passive speaker; audio rating is not mains demand | 10 | -90 | -26.4631 | [10 empty] | Current | drop:AV1:A3:audio:-1:S286 | {"dim":1,"level":-6,"delayMs":25}
S287 | Courtyard horn · H | speaker | DB1 | A3 | -0.14 | 6.2 | 8.3 | wall | Shown | Off | 420 × 400 × 400 | 30 W audio rating · Passive / amplifier output · 100.3 ms delay. Passive speaker; audio rating is not mains demand | 10 | -172.1256 | -14.4345 | [10 empty] | Current | drop:AV1:A3:audio:1:S287 | {"dim":1,"level":-4,"delayMs":100.3}
S288 | Tower horn · H · outer | speaker | DB1 | A3 | -0.14 | 6.2 | 11.9 | wall | Shown | Off | 420 × 400 × 400 | 30 W audio rating · Passive / amplifier output · 92.2 ms delay. Passive speaker; audio rating is not mains demand | 10 | 172.5973 | -14.4498 | [10 empty] | Current | drop:AV1:A3:audio:1:S288 | {"dim":1,"level":-4,"delayMs":92.2}
S289 | Side courtyard horn · axis 5 · H | speaker | DB1 | A3 | 18.975 | 5.6 | 10.75 | wall | Shown | Off | 420 × 400 × 400 | 30 W audio rating · Passive / amplifier output · 66.4 ms delay. Passive speaker; audio rating is not mains demand | 10 | 90 | -26.4631 | [10 empty] | Current | drop:AV1:A3:audio:1:S289 | {"dim":1,"level":-6,"delayMs":66.4}
S290 | Side courtyard horn · axis 8 · H | speaker | DB1 | A3 | 32.475 | 5.6 | 10.75 | wall | Shown | Off | 420 × 400 × 400 | 30 W audio rating · Passive / amplifier output · 33.6 ms delay. Passive speaker; audio rating is not mains demand | 10 | 90 | -26.4631 | [10 empty] | Current | drop:AV1:A3:audio:1:S290 | {"dim":1,"level":-6,"delayMs":33.6}
S291 | Ambo microphone | speaker | DB1 | MIC | 41.08 | 1.9 | -2.62 | floor | Shown | On | 362 × 374 × 120 | Microphone signal → mixer input | 0 | 0 | 0 | [10 empty] | Current | drop:AV1:MIC:mic:-1:S291 | {"dim":1}
S292 | Altar microphone | speaker | DB1 | MIC | 44.45 | 1.88 | 0.45 | floor | Shown | On | 362 × 374 × 120 | Microphone signal → mixer input | 0 | 0 | 0 | [10 empty] | Current | drop:AV1:MIC:mic:1:S292 | {"dim":1}
S275 | Wing speaker · B · front block | speaker | DB1 | A1 | 38.94 | 3 | -11.6 | pendant | Shown | On | 367 × 257 × 260 | 30 W audio rating · Passive / amplifier output · 25.2 ms delay. Passive speaker; audio rating is not mains demand | 10 | 90 | -46.3972 | [10 empty] | Retired | drop:AV1:A1:audio:-1:S275 | {"dim":1,"level":-10,"delayMs":25.2,"anchorY":8.115059999999996}
S277 | Wing speaker · H · front block | speaker | DB1 | A1 | 38.94 | 3 | 11.6 | pendant | Shown | On | 367 × 257 × 260 | 30 W audio rating · Passive / amplifier output · 39.4 ms delay. Passive speaker; audio rating is not mains demand | 10 | -90 | -46.3972 | [10 empty] | Retired | drop:AV1:A1:audio:1:S277 | {"dim":1,"level":-10,"delayMs":39.4,"anchorY":8.115059999999996}

## Electrical Lines
Electrical line register
Model fields refresh from matching layout exports. Amber columns are retained engineering inputs.
Lengths are geometric. Blank allowance means installed length is pending. Shared bundles are not extra home-run cable.
Filter by ID, board, circuit or status. Retired rows retain prior engineering inputs.
Route ID | Name | Source ID | Destination IDs | Board | Circuit | Kind | Role | Route length (m) | Upstream length (m) | Full home run (m) | Length basis | Allowance (m) | Planned length (m) | Planning specification | Installation proposal | Cable designation | Core count | Cross-section (mm2) | Containment specification | Manufacturer / product | Control / terminal reference | Approval reference | Engineering notes | Record state | Trunk ID
trunk:AV1:A1:audio:-1 | A1 · B · audio home-run bundle | AV1 | S261 S263 S265 S267 S269 S271 S276 | DB1 | A1 | audio | trunk | 61.2741 |  |  | Shared bundle |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Wall bands above openings; concealed finish-matched soffit crossing over the 9–10 wing opening. | [8 empty] | Current
drop:AV1:A1:audio:-1:S261 | A1 → Wall speaker · axis 4 · B | AV1 | S261 | DB1 | A1 | audio | drop | 2.534 | 61.2741 | 63.8081 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Concealed solid-pier / wall drop and local termination. | [8 empty] | Current | trunk:AV1:A1:audio:-1
drop:AV1:A1:audio:-1:S263 | A1 → Wall speaker · axis 5 · B | AV1 | S263 | DB1 | A1 | audio | drop | 2.534 | 56.7741 | 59.3081 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Concealed solid-pier / wall drop and local termination. | [8 empty] | Current | trunk:AV1:A1:audio:-1
drop:AV1:A1:audio:-1:S265 | A1 → Wall speaker · axis 6 · B | AV1 | S265 | DB1 | A1 | audio | drop | 2.534 | 52.2741 | 54.8081 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Concealed solid-pier / wall drop and local termination. | [8 empty] | Current | trunk:AV1:A1:audio:-1
drop:AV1:A1:audio:-1:S267 | A1 → Wall speaker · axis 7 · B | AV1 | S267 | DB1 | A1 | audio | drop | 2.534 | 47.7741 | 50.3081 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Concealed solid-pier / wall drop and local termination. | [8 empty] | Current | trunk:AV1:A1:audio:-1
drop:AV1:A1:audio:-1:S269 | A1 → Wall speaker · axis 8 · B | AV1 | S269 | DB1 | A1 | audio | drop | 2.534 | 43.2741 | 45.8081 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Concealed solid-pier / wall drop and local termination. | [8 empty] | Current | trunk:AV1:A1:audio:-1
drop:AV1:A1:audio:-1:S271 | A1 → Wall speaker · axis 9 · B | AV1 | S271 | DB1 | A1 | audio | drop | 2.534 | 38.7741 | 41.3081 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Concealed solid-pier / wall drop and local termination. | [8 empty] | Current | trunk:AV1:A1:audio:-1
drop:AV1:A1:audio:-1:S276 | A1 → Wing speaker · B · toward entrance · held | AV1 | S276 | DB1 | A1 | audio | drop | 8.0407 | 28.967 | 37.0077 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Covered roof-soffit crossing into outer arcade / wing-gable wall, then concealed pier drop. No exposed crossing at equipment height. | [8 empty] | Current | trunk:AV1:A1:audio:-1
trunk:AV1:A1:audio:1 | A1 · H · audio home-run bundle | AV1 | S262 S264 S266 S268 S270 S272 S278 | DB1 | A1 | audio | trunk | 67.8741 |  |  | Shared bundle |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Wall bands above openings; concealed finish-matched soffit crossing over the 9–10 wing opening. | [8 empty] | Current
drop:AV1:A1:audio:1:S262 | A1 → Wall speaker · axis 4 · H | AV1 | S262 | DB1 | A1 | audio | drop | 2.534 | 67.8741 | 70.4081 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Concealed solid-pier / wall drop and local termination. | [8 empty] | Current | trunk:AV1:A1:audio:1
drop:AV1:A1:audio:1:S264 | A1 → Wall speaker · axis 5 · H | AV1 | S264 | DB1 | A1 | audio | drop | 2.534 | 63.3741 | 65.9081 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Concealed solid-pier / wall drop and local termination. | [8 empty] | Current | trunk:AV1:A1:audio:1
drop:AV1:A1:audio:1:S266 | A1 → Wall speaker · axis 6 · H | AV1 | S266 | DB1 | A1 | audio | drop | 2.534 | 58.8741 | 61.4081 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Concealed solid-pier / wall drop and local termination. | [8 empty] | Current | trunk:AV1:A1:audio:1
drop:AV1:A1:audio:1:S268 | A1 → Wall speaker · axis 7 · H | AV1 | S268 | DB1 | A1 | audio | drop | 2.534 | 54.3741 | 56.9081 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Concealed solid-pier / wall drop and local termination. | [8 empty] | Current | trunk:AV1:A1:audio:1
drop:AV1:A1:audio:1:S270 | A1 → Wall speaker · axis 8 · H | AV1 | S270 | DB1 | A1 | audio | drop | 2.534 | 49.8741 | 52.4081 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Concealed solid-pier / wall drop and local termination. | [8 empty] | Current | trunk:AV1:A1:audio:1
drop:AV1:A1:audio:1:S272 | A1 → Wall speaker · axis 9 · H | AV1 | S272 | DB1 | A1 | audio | drop | 2.534 | 45.3741 | 47.9081 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Concealed solid-pier / wall drop and local termination. | [8 empty] | Current | trunk:AV1:A1:audio:1
drop:AV1:A1:audio:1:S278 | A1 → Wing speaker · H · toward entrance · held | AV1 | S278 | DB1 | A1 | audio | drop | 8.0407 | 35.567 | 43.6077 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Covered roof-soffit crossing into outer arcade / wing-gable wall, then concealed pier drop. No exposed crossing at equipment height. | [8 empty] | Current | trunk:AV1:A1:audio:1
trunk:AV1:A5:audio:-1 | A5 · B · audio home-run bundle | AV1 | S273 | DB1 | A5 | audio | trunk | 73.0621 |  |  | Shared bundle |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Wall bands above openings; concealed finish-matched soffit crossing over the 9–10 wing opening. | [8 empty] | Current
drop:AV1:A5:audio:-1:S273 | A5 → Wall speaker · entrance hall · B | AV1 | S273 | DB1 | A5 | audio | drop | 10.613 | 73.0621 | 83.6752 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Concealed entrance wall band, solid pier and local termination. | [8 empty] | Current | trunk:AV1:A5:audio:-1
trunk:AV1:A5:audio:1 | A5 · H · audio home-run bundle | AV1 | S274 | DB1 | A5 | audio | trunk | 79.6621 |  |  | Shared bundle |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Wall bands above openings; concealed finish-matched soffit crossing over the 9–10 wing opening. | [8 empty] | Current
drop:AV1:A5:audio:1:S274 | A5 → Wall speaker · entrance hall · H | AV1 | S274 | DB1 | A5 | audio | drop | 10.613 | 79.6621 | 90.2752 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Concealed entrance wall band, solid pier and local termination. | [8 empty] | Current | trunk:AV1:A5:audio:1
trunk:AV1:A2:audio:-1 | A2 · B · audio home-run bundle | AV1 | S279 S280 | DB1 | A2 | audio | trunk | 62.2111 |  |  | Shared bundle |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Wall bands above openings; concealed finish-matched soffit crossing over the 9–10 wing opening. | [8 empty] | Current
drop:AV1:A2:audio:-1:S279 | A2 → Veranda fill · B · 12.2 | AV1 | S279 | DB1 | A2 | audio | drop | 6.9407 | 62.2111 | 69.1519 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Above nave lining / covered soffit route at wings and verandas; cable continues inside the existing pendant stem. Roof build-up, supports and access pending. | [8 empty] | Current | trunk:AV1:A2:audio:-1
drop:AV1:A2:audio:-1:S280 | A2 → Veranda fill · B · 25.7 | AV1 | S280 | DB1 | A2 | audio | drop | 6.9407 | 48.7111 | 55.6519 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Above nave lining / covered soffit route at wings and verandas; cable continues inside the existing pendant stem. Roof build-up, supports and access pending. | [8 empty] | Current | trunk:AV1:A2:audio:-1
trunk:AV1:A2:audio:1 | A2 · H · audio home-run bundle | AV1 | S281 S282 | DB1 | A2 | audio | trunk | 68.8111 |  |  | Shared bundle |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Wall bands above openings; concealed finish-matched soffit crossing over the 9–10 wing opening. | [8 empty] | Current
drop:AV1:A2:audio:1:S281 | A2 → Veranda fill · H · 12.2 | AV1 | S281 | DB1 | A2 | audio | drop | 6.9407 | 68.8111 | 75.7519 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Above nave lining / covered soffit route at wings and verandas; cable continues inside the existing pendant stem. Roof build-up, supports and access pending. | [8 empty] | Current | trunk:AV1:A2:audio:1
drop:AV1:A2:audio:1:S282 | A2 → Veranda fill · H · 25.7 | AV1 | S282 | DB1 | A2 | audio | drop | 6.9407 | 55.3111 | 62.2519 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Above nave lining / covered soffit route at wings and verandas; cable continues inside the existing pendant stem. Roof build-up, supports and access pending. | [8 empty] | Current | trunk:AV1:A2:audio:1
trunk:AV1:A3:audio:-1 | A3 · B · audio home-run bundle | AV1 | S283 S284 S285 S286 | DB1 | A3 | audio | trunk | 73.3831 |  |  | Shared bundle |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Wall bands above openings; concealed finish-matched soffit crossing over the 9–10 wing opening. | [8 empty] | Current
drop:AV1:A3:audio:-1:S283 | A3 → Courtyard horn · B | AV1 | S283 | DB1 | A3 | audio | drop | 6.82 | 73.3831 | 80.2031 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Solid tower corner/piers, stepped behind cornices; local ledge/fitting connection. No riser through louver openings; chase/finish and weathering details pending. | [8 empty] | Current | trunk:AV1:A3:audio:-1
drop:AV1:A3:audio:-1:S284 | A3 → Tower horn · B · outer | AV1 | S284 | DB1 | A3 | audio | drop | 11.346 | 73.3831 | 84.7291 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Solid tower corner/piers, stepped behind cornices; local ledge/fitting connection. No riser through louver openings; chase/finish and weathering details pending. | [8 empty] | Current | trunk:AV1:A3:audio:-1
drop:AV1:A3:audio:-1:S285 | A3 → Side courtyard horn · axis 5 · B | AV1 | S285 | DB1 | A3 | audio | drop | 5.5182 | 56.7581 | 62.2763 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Covered roof-soffit crossing into outer arcade / wing-gable wall, then concealed pier drop. No exposed crossing at equipment height. | [8 empty] | Current | trunk:AV1:A3:audio:-1
drop:AV1:A3:audio:-1:S286 | A3 → Side courtyard horn · axis 8 · B | AV1 | S286 | DB1 | A3 | audio | drop | 5.5182 | 43.2581 | 48.7763 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Covered roof-soffit crossing into outer arcade / wing-gable wall, then concealed pier drop. No exposed crossing at equipment height. | [8 empty] | Current | trunk:AV1:A3:audio:-1
trunk:AV1:A3:audio:1 | A3 · H · audio home-run bundle | AV1 | S287 S288 S289 S290 | DB1 | A3 | audio | trunk | 79.9831 |  |  | Shared bundle |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Wall bands above openings; concealed finish-matched soffit crossing over the 9–10 wing opening. | [8 empty] | Current
drop:AV1:A3:audio:1:S287 | A3 → Courtyard horn · H | AV1 | S287 | DB1 | A3 | audio | drop | 6.82 | 79.9831 | 86.8031 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Solid tower corner/piers, stepped behind cornices; local ledge/fitting connection. No riser through louver openings; chase/finish and weathering details pending. | [8 empty] | Current | trunk:AV1:A3:audio:1
drop:AV1:A3:audio:1:S288 | A3 → Tower horn · H · outer | AV1 | S288 | DB1 | A3 | audio | drop | 11.346 | 79.9831 | 91.3291 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Solid tower corner/piers, stepped behind cornices; local ledge/fitting connection. No riser through louver openings; chase/finish and weathering details pending. | [8 empty] | Current | trunk:AV1:A3:audio:1
drop:AV1:A3:audio:1:S289 | A3 → Side courtyard horn · axis 5 · H | AV1 | S289 | DB1 | A3 | audio | drop | 5.5182 | 63.3581 | 68.8763 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Covered roof-soffit crossing into outer arcade / wing-gable wall, then concealed pier drop. No exposed crossing at equipment height. | [8 empty] | Current | trunk:AV1:A3:audio:1
drop:AV1:A3:audio:1:S290 | A3 → Side courtyard horn · axis 8 · H | AV1 | S290 | DB1 | A3 | audio | drop | 5.5182 | 49.8581 | 55.3763 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Covered roof-soffit crossing into outer arcade / wing-gable wall, then concealed pier drop. No exposed crossing at equipment height. | [8 empty] | Current | trunk:AV1:A3:audio:1
trunk:AV1:MIC:mic:-1 | MIC · B · audio home-run bundle | AV1 | S291 | DB1 | MIC | mic | trunk | 11.915 |  |  | Shared bundle |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Separate microphone home-run bundle below service-room and sanctuary floors; floor build-up / access pending. | [8 empty] | Current
drop:AV1:MIC:mic:-1:S291 | MIC → Ambo microphone | AV1 | S291 | DB1 | MIC | mic | drop | 3.5791 | 11.915 | 15.4941 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Separate AV-1 home run below floor; central ambo passage through proposed hollow neck, sloped desk and removable microphone socket. Floorbox, furniture bore and access pending. | [8 empty] | Current | trunk:AV1:MIC:mic:-1
trunk:AV1:MIC:mic:1 | MIC · H · audio home-run bundle | AV1 | S292 | DB1 | MIC | mic | trunk | 5.745 |  |  | Shared bundle |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Separate microphone home-run bundle below service-room and sanctuary floors; floor build-up / access pending. | [8 empty] | Current
drop:AV1:MIC:mic:1:S292 | MIC → Altar microphone | AV1 | S292 | DB1 | MIC | mic | drop | 2.8 | 5.745 | 8.545 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Separate AV-1 home run below the floor; proposed furniture cable passage to microphone base. Floorbox, floor build-up and furniture access pending. | [8 empty] | Current | trunk:AV1:MIC:mic:1
drop:AV1:A1:audio:-1:S275 | A1 → Wing speaker · B · front block | AV1 | S275 | DB1 | A1 | audio | drop | 9.1932 | 35.0694 | 44.2626 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Above nave lining / covered soffit route at wings and verandas; cable continues inside the existing pendant stem. Roof build-up, supports and access pending. | [8 empty] | Retired | trunk:AV1:A1:audio:-1
drop:AV1:A1:audio:1:S277 | A1 → Wing speaker · H · front block | AV1 | S277 | DB1 | A1 | audio | drop | 9.1932 | 41.6694 | 50.8626 | Full home run |  |  | Cable type / conductors / cross-section / conduit: pending electrical design | Above nave lining / covered soffit route at wings and verandas; cable continues inside the existing pendant stem. Roof build-up, supports and access pending. | [8 empty] | Retired | trunk:AV1:A1:audio:1

## Route Points
Route vertices in the shared layout
Model fields refresh from matching layout exports. Amber columns are retained engineering inputs.
Each route uses these ordered X/Y/Z vertices in metres. Segment lengths are calculated from adjacent vertices.
Filter by ID, board, circuit or status. Retired rows retain prior engineering inputs.
Route ID | Vertex | X (m) | Y (m) | Z (m) | Segment length (m) | Record state
trunk:AV1:A1:audio:-1 | 1 | 49.275 | 0.95 | 1.4 | 0 | Current
trunk:AV1:A1:audio:-1 | 2 | 48.735 | 0.95 | 1.4 | 0.54 | Current
trunk:AV1:A1:audio:-1 | 3 | 48.735 | 0.95 | -2.24 | 3.64 | Current
trunk:AV1:A1:audio:-1 | 4 | 48.735 | 4.33 | -2.24 | 3.38 | Current
trunk:AV1:A1:audio:-1 | 5 | 48.735 | 4.33 | -3.3 | 1.06 | Current
trunk:AV1:A1:audio:-1 | 6 | 53.016 | 4.33 | -3.3 | 4.281 | Current
trunk:AV1:A1:audio:-1 | 7 | 53.016 | 5.694 | -3.3 | 1.364 | Current
trunk:AV1:A1:audio:-1 | 8 | 53.016 | 5.694 | -7.36 | 4.06 | Current
trunk:AV1:A1:audio:-1 | 9 | 44.175 | 5.694 | -7.36 | 8.841 | Current
trunk:AV1:A1:audio:-1 | 10 | 44.175 | 7.04 | -7.36 | 1.346 | Current
trunk:AV1:A1:audio:-1 | 11 | 43.535 | 7.04 | -7.36 | 0.64 | Current
trunk:AV1:A1:audio:-1 | 12 | 43.455 | 6.9504 | -7.36 | 0.12011 | Current
trunk:AV1:A1:audio:-1 | 13 | 40.575 | 9.27 | -7.36 | 3.698 | Current
trunk:AV1:A1:audio:-1 | 14 | 37.695 | 6.9504 | -7.36 | 3.698 | Current
trunk:AV1:A1:audio:-1 | 15 | 37.615 | 7.04 | -7.36 | 0.12011 | Current
trunk:AV1:A1:audio:-1 | 16 | 36.975 | 7.04 | -7.36 | 0.64 | Current
trunk:AV1:A1:audio:-1 | 17 | 36.975 | 5.694 | -7.36 | 1.346 | Current
trunk:AV1:A1:audio:-1 | 18 | 14.475 | 5.694 | -7.36 | 22.5 | Current
drop:AV1:A1:audio:-1:S261 | 1 | 14.475 | 5.694 | -7.36 | 0 | Current
drop:AV1:A1:audio:-1:S261 | 2 | 14.475 | 3.45 | -7.36 | 2.244 | Current
drop:AV1:A1:audio:-1:S261 | 3 | 14.475 | 3.45 | -7.07 | 0.29 | Current
drop:AV1:A1:audio:-1:S263 | 1 | 18.975 | 5.694 | -7.36 | 0 | Current
drop:AV1:A1:audio:-1:S263 | 2 | 18.975 | 3.45 | -7.36 | 2.244 | Current
drop:AV1:A1:audio:-1:S263 | 3 | 18.975 | 3.45 | -7.07 | 0.29 | Current
drop:AV1:A1:audio:-1:S265 | 1 | 23.475 | 5.694 | -7.36 | 0 | Current
drop:AV1:A1:audio:-1:S265 | 2 | 23.475 | 3.45 | -7.36 | 2.244 | Current
drop:AV1:A1:audio:-1:S265 | 3 | 23.475 | 3.45 | -7.07 | 0.29 | Current
drop:AV1:A1:audio:-1:S267 | 1 | 27.975 | 5.694 | -7.36 | 0 | Current
drop:AV1:A1:audio:-1:S267 | 2 | 27.975 | 3.45 | -7.36 | 2.244 | Current
drop:AV1:A1:audio:-1:S267 | 3 | 27.975 | 3.45 | -7.07 | 0.29 | Current
drop:AV1:A1:audio:-1:S269 | 1 | 32.475 | 5.694 | -7.36 | 0 | Current
drop:AV1:A1:audio:-1:S269 | 2 | 32.475 | 3.45 | -7.36 | 2.244 | Current
drop:AV1:A1:audio:-1:S269 | 3 | 32.475 | 3.45 | -7.07 | 0.29 | Current
drop:AV1:A1:audio:-1:S271 | 1 | 36.975 | 5.694 | -7.36 | 0 | Current
drop:AV1:A1:audio:-1:S271 | 2 | 36.975 | 3.45 | -7.36 | 2.244 | Current
drop:AV1:A1:audio:-1:S271 | 3 | 36.975 | 3.45 | -7.07 | 0.29 | Current
drop:AV1:A1:audio:-1:S276 | 1 | 43.72 | 7.04 | -7.36 | 0 | Current
drop:AV1:A1:audio:-1:S276 | 2 | 43.72 | 6.9323 | -7.4396 | 0.13391 | Current
drop:AV1:A1:audio:-1:S276 | 3 | 43.72 | 6.7376 | -8.315 | 0.89678 | Current
drop:AV1:A1:audio:-1:S276 | 4 | 43.72 | 6.737 | -8.3946 | 0.079584 | Current
drop:AV1:A1:audio:-1:S276 | 5 | 43.72 | 6.737 | -13.249 | 4.8544 | Current
drop:AV1:A1:audio:-1:S276 | 6 | 43.72 | 4.85 | -13.249 | 1.887 | Current
drop:AV1:A1:audio:-1:S276 | 7 | 43.72 | 4.85 | -13.06 | 0.189 | Current
trunk:AV1:A1:audio:1 | 1 | 49.275 | 0.95 | 1.4 | 0 | Current
trunk:AV1:A1:audio:1 | 2 | 48.735 | 0.95 | 1.4 | 0.54 | Current
trunk:AV1:A1:audio:1 | 3 | 48.735 | 0.95 | -2.24 | 3.64 | Current
trunk:AV1:A1:audio:1 | 4 | 48.735 | 4.33 | -2.24 | 3.38 | Current
trunk:AV1:A1:audio:1 | 5 | 48.735 | 4.33 | -3.3 | 1.06 | Current
trunk:AV1:A1:audio:1 | 6 | 53.016 | 4.33 | -3.3 | 4.281 | Current
trunk:AV1:A1:audio:1 | 7 | 53.016 | 5.694 | -3.3 | 1.364 | Current
trunk:AV1:A1:audio:1 | 8 | 53.016 | 5.694 | 7.36 | 10.66 | Current
trunk:AV1:A1:audio:1 | 9 | 44.175 | 5.694 | 7.36 | 8.841 | Current
trunk:AV1:A1:audio:1 | 10 | 44.175 | 7.04 | 7.36 | 1.346 | Current
trunk:AV1:A1:audio:1 | 11 | 43.535 | 7.04 | 7.36 | 0.64 | Current
trunk:AV1:A1:audio:1 | 12 | 43.455 | 6.9504 | 7.36 | 0.12011 | Current
trunk:AV1:A1:audio:1 | 13 | 40.575 | 9.27 | 7.36 | 3.698 | Current
trunk:AV1:A1:audio:1 | 14 | 37.695 | 6.9504 | 7.36 | 3.698 | Current
trunk:AV1:A1:audio:1 | 15 | 37.615 | 7.04 | 7.36 | 0.12011 | Current
trunk:AV1:A1:audio:1 | 16 | 36.975 | 7.04 | 7.36 | 0.64 | Current
trunk:AV1:A1:audio:1 | 17 | 36.975 | 5.694 | 7.36 | 1.346 | Current
trunk:AV1:A1:audio:1 | 18 | 14.475 | 5.694 | 7.36 | 22.5 | Current
drop:AV1:A1:audio:1:S262 | 1 | 14.475 | 5.694 | 7.36 | 0 | Current
drop:AV1:A1:audio:1:S262 | 2 | 14.475 | 3.45 | 7.36 | 2.244 | Current
drop:AV1:A1:audio:1:S262 | 3 | 14.475 | 3.45 | 7.07 | 0.29 | Current
drop:AV1:A1:audio:1:S264 | 1 | 18.975 | 5.694 | 7.36 | 0 | Current
drop:AV1:A1:audio:1:S264 | 2 | 18.975 | 3.45 | 7.36 | 2.244 | Current
drop:AV1:A1:audio:1:S264 | 3 | 18.975 | 3.45 | 7.07 | 0.29 | Current
drop:AV1:A1:audio:1:S266 | 1 | 23.475 | 5.694 | 7.36 | 0 | Current
drop:AV1:A1:audio:1:S266 | 2 | 23.475 | 3.45 | 7.36 | 2.244 | Current
drop:AV1:A1:audio:1:S266 | 3 | 23.475 | 3.45 | 7.07 | 0.29 | Current
drop:AV1:A1:audio:1:S268 | 1 | 27.975 | 5.694 | 7.36 | 0 | Current
drop:AV1:A1:audio:1:S268 | 2 | 27.975 | 3.45 | 7.36 | 2.244 | Current
drop:AV1:A1:audio:1:S268 | 3 | 27.975 | 3.45 | 7.07 | 0.29 | Current
drop:AV1:A1:audio:1:S270 | 1 | 32.475 | 5.694 | 7.36 | 0 | Current
drop:AV1:A1:audio:1:S270 | 2 | 32.475 | 3.45 | 7.36 | 2.244 | Current
drop:AV1:A1:audio:1:S270 | 3 | 32.475 | 3.45 | 7.07 | 0.29 | Current
drop:AV1:A1:audio:1:S272 | 1 | 36.975 | 5.694 | 7.36 | 0 | Current
drop:AV1:A1:audio:1:S272 | 2 | 36.975 | 3.45 | 7.36 | 2.244 | Current
drop:AV1:A1:audio:1:S272 | 3 | 36.975 | 3.45 | 7.07 | 0.29 | Current
drop:AV1:A1:audio:1:S278 | 1 | 43.72 | 7.04 | 7.36 | 0 | Current
drop:AV1:A1:audio:1:S278 | 2 | 43.72 | 6.9323 | 7.4396 | 0.13391 | Current
drop:AV1:A1:audio:1:S278 | 3 | 43.72 | 6.7376 | 8.315 | 0.89678 | Current
drop:AV1:A1:audio:1:S278 | 4 | 43.72 | 6.737 | 8.3946 | 0.079584 | Current
drop:AV1:A1:audio:1:S278 | 5 | 43.72 | 6.737 | 13.249 | 4.8544 | Current
drop:AV1:A1:audio:1:S278 | 6 | 43.72 | 4.85 | 13.249 | 1.887 | Current
drop:AV1:A1:audio:1:S278 | 7 | 43.72 | 4.85 | 13.06 | 0.189 | Current
trunk:AV1:A5:audio:-1 | 1 | 49.275 | 0.95 | 1.4 | 0 | Current
trunk:AV1:A5:audio:-1 | 2 | 48.735 | 0.95 | 1.4 | 0.54 | Current
trunk:AV1:A5:audio:-1 | 3 | 48.735 | 0.95 | -2.24 | 3.64 | Current
trunk:AV1:A5:audio:-1 | 4 | 48.735 | 4.33 | -2.24 | 3.38 | Current
trunk:AV1:A5:audio:-1 | 5 | 48.735 | 4.33 | -3.3 | 1.06 | Current
trunk:AV1:A5:audio:-1 | 6 | 53.016 | 4.33 | -3.3 | 4.281 | Current
trunk:AV1:A5:audio:-1 | 7 | 53.016 | 5.726 | -3.3 | 1.396 | Current
trunk:AV1:A5:audio:-1 | 8 | 53.016 | 5.726 | -7.36 | 4.06 | Current
trunk:AV1:A5:audio:-1 | 9 | 44.175 | 5.726 | -7.36 | 8.841 | Current
trunk:AV1:A5:audio:-1 | 10 | 44.175 | 7.04 | -7.36 | 1.314 | Current
trunk:AV1:A5:audio:-1 | 11 | 43.535 | 7.04 | -7.36 | 0.64 | Current
trunk:AV1:A5:audio:-1 | 12 | 43.455 | 6.9504 | -7.36 | 0.12011 | Current
trunk:AV1:A5:audio:-1 | 13 | 40.575 | 9.27 | -7.36 | 3.698 | Current
trunk:AV1:A5:audio:-1 | 14 | 37.695 | 6.9504 | -7.36 | 3.698 | Current
trunk:AV1:A5:audio:-1 | 15 | 37.615 | 7.04 | -7.36 | 0.12011 | Current
trunk:AV1:A5:audio:-1 | 16 | 36.975 | 7.04 | -7.36 | 0.64 | Current
trunk:AV1:A5:audio:-1 | 17 | 36.975 | 5.726 | -7.36 | 1.314 | Current
trunk:AV1:A5:audio:-1 | 18 | 5.475 | 5.726 | -7.36 | 31.5 | Current
trunk:AV1:A5:audio:-1 | 19 | 2.655 | 5.726 | -7.36 | 2.82 | Current
drop:AV1:A5:audio:-1:S273 | 1 | 2.655 | 5.726 | -7.36 | 0 | Current
drop:AV1:A5:audio:-1:S273 | 2 | 2.35 | 7.65 | -7.36 | 1.948 | Current
drop:AV1:A5:audio:-1:S273 | 3 | 2.35 | 7.65 | -3.05 | 4.31 | Current
drop:AV1:A5:audio:-1:S273 | 4 | 2.35 | 3.6 | -3.05 | 4.05 | Current
drop:AV1:A5:audio:-1:S273 | 5 | 2.655 | 3.6 | -3.05 | 0.305 | Current
trunk:AV1:A5:audio:1 | 1 | 49.275 | 0.95 | 1.4 | 0 | Current
trunk:AV1:A5:audio:1 | 2 | 48.735 | 0.95 | 1.4 | 0.54 | Current
trunk:AV1:A5:audio:1 | 3 | 48.735 | 0.95 | -2.24 | 3.64 | Current
trunk:AV1:A5:audio:1 | 4 | 48.735 | 4.33 | -2.24 | 3.38 | Current
trunk:AV1:A5:audio:1 | 5 | 48.735 | 4.33 | -3.3 | 1.06 | Current
trunk:AV1:A5:audio:1 | 6 | 53.016 | 4.33 | -3.3 | 4.281 | Current
trunk:AV1:A5:audio:1 | 7 | 53.016 | 5.726 | -3.3 | 1.396 | Current
trunk:AV1:A5:audio:1 | 8 | 53.016 | 5.726 | 7.36 | 10.66 | Current
trunk:AV1:A5:audio:1 | 9 | 44.175 | 5.726 | 7.36 | 8.841 | Current
trunk:AV1:A5:audio:1 | 10 | 44.175 | 7.04 | 7.36 | 1.314 | Current
trunk:AV1:A5:audio:1 | 11 | 43.535 | 7.04 | 7.36 | 0.64 | Current
trunk:AV1:A5:audio:1 | 12 | 43.455 | 6.9504 | 7.36 | 0.12011 | Current
trunk:AV1:A5:audio:1 | 13 | 40.575 | 9.27 | 7.36 | 3.698 | Current
trunk:AV1:A5:audio:1 | 14 | 37.695 | 6.9504 | 7.36 | 3.698 | Current
trunk:AV1:A5:audio:1 | 15 | 37.615 | 7.04 | 7.36 | 0.12011 | Current
trunk:AV1:A5:audio:1 | 16 | 36.975 | 7.04 | 7.36 | 0.64 | Current
trunk:AV1:A5:audio:1 | 17 | 36.975 | 5.726 | 7.36 | 1.314 | Current
trunk:AV1:A5:audio:1 | 18 | 5.475 | 5.726 | 7.36 | 31.5 | Current
trunk:AV1:A5:audio:1 | 19 | 2.655 | 5.726 | 7.36 | 2.82 | Current
drop:AV1:A5:audio:1:S274 | 1 | 2.655 | 5.726 | 7.36 | 0 | Current
drop:AV1:A5:audio:1:S274 | 2 | 2.35 | 7.65 | 7.36 | 1.948 | Current
drop:AV1:A5:audio:1:S274 | 3 | 2.35 | 7.65 | 3.05 | 4.31 | Current
drop:AV1:A5:audio:1:S274 | 4 | 2.35 | 3.6 | 3.05 | 4.05 | Current
drop:AV1:A5:audio:1:S274 | 5 | 2.655 | 3.6 | 3.05 | 0.305 | Current
trunk:AV1:A2:audio:-1 | 1 | 49.275 | 0.95 | 1.4 | 0 | Current
trunk:AV1:A2:audio:-1 | 2 | 48.735 | 0.95 | 1.4 | 0.54 | Current
trunk:AV1:A2:audio:-1 | 3 | 48.735 | 0.95 | -2.24 | 3.64 | Current
trunk:AV1:A2:audio:-1 | 4 | 48.735 | 4.33 | -2.24 | 3.38 | Current
trunk:AV1:A2:audio:-1 | 5 | 48.735 | 4.33 | -3.3 | 1.06 | Current
trunk:AV1:A2:audio:-1 | 6 | 53.016 | 4.33 | -3.3 | 4.281 | Current
trunk:AV1:A2:audio:-1 | 7 | 53.016 | 5.702 | -3.3 | 1.372 | Current
trunk:AV1:A2:audio:-1 | 8 | 53.016 | 5.702 | -7.36 | 4.06 | Current
trunk:AV1:A2:audio:-1 | 9 | 44.175 | 5.702 | -7.36 | 8.841 | Current
trunk:AV1:A2:audio:-1 | 10 | 44.175 | 7.04 | -7.36 | 1.338 | Current
trunk:AV1:A2:audio:-1 | 11 | 43.535 | 7.04 | -7.36 | 0.64 | Current
trunk:AV1:A2:audio:-1 | 12 | 43.455 | 6.9504 | -7.36 | 0.12011 | Current
trunk:AV1:A2:audio:-1 | 13 | 40.575 | 9.27 | -7.36 | 3.698 | Current
trunk:AV1:A2:audio:-1 | 14 | 37.695 | 6.9504 | -7.36 | 3.698 | Current
trunk:AV1:A2:audio:-1 | 15 | 37.615 | 7.04 | -7.36 | 0.12011 | Current
trunk:AV1:A2:audio:-1 | 16 | 36.975 | 7.04 | -7.36 | 0.64 | Current
trunk:AV1:A2:audio:-1 | 17 | 36.975 | 5.702 | -7.36 | 1.338 | Current
trunk:AV1:A2:audio:-1 | 18 | 13.53 | 5.702 | -7.36 | 23.445 | Current
drop:AV1:A2:audio:-1:S279 | 1 | 13.53 | 5.702 | -7.36 | 0 | Current
drop:AV1:A2:audio:-1:S279 | 2 | 13.53 | 7.04 | -7.36 | 1.338 | Current
drop:AV1:A2:audio:-1:S279 | 3 | 12.225 | 7.04 | -7.36 | 1.305 | Current
drop:AV1:A2:audio:-1:S279 | 4 | 12.225 | 6.9326 | -7.4384 | 0.13301 | Current
drop:AV1:A2:audio:-1:S279 | 5 | 12.225 | 6.6187 | -8.85 | 1.4461 | Current
drop:AV1:A2:audio:-1:S279 | 6 | 12.225 | 3.9 | -8.85 | 2.7187 | Current
drop:AV1:A2:audio:-1:S280 | 1 | 27.03 | 5.702 | -7.36 | 0 | Current
drop:AV1:A2:audio:-1:S280 | 2 | 27.03 | 7.04 | -7.36 | 1.338 | Current
drop:AV1:A2:audio:-1:S280 | 3 | 25.725 | 7.04 | -7.36 | 1.305 | Current
drop:AV1:A2:audio:-1:S280 | 4 | 25.725 | 6.9326 | -7.4384 | 0.13301 | Current
drop:AV1:A2:audio:-1:S280 | 5 | 25.725 | 6.6187 | -8.85 | 1.4461 | Current
drop:AV1:A2:audio:-1:S280 | 6 | 25.725 | 3.9 | -8.85 | 2.7187 | Current
trunk:AV1:A2:audio:1 | 1 | 49.275 | 0.95 | 1.4 | 0 | Current
trunk:AV1:A2:audio:1 | 2 | 48.735 | 0.95 | 1.4 | 0.54 | Current
trunk:AV1:A2:audio:1 | 3 | 48.735 | 0.95 | -2.24 | 3.64 | Current
trunk:AV1:A2:audio:1 | 4 | 48.735 | 4.33 | -2.24 | 3.38 | Current
trunk:AV1:A2:audio:1 | 5 | 48.735 | 4.33 | -3.3 | 1.06 | Current
trunk:AV1:A2:audio:1 | 6 | 53.016 | 4.33 | -3.3 | 4.281 | Current
trunk:AV1:A2:audio:1 | 7 | 53.016 | 5.702 | -3.3 | 1.372 | Current
trunk:AV1:A2:audio:1 | 8 | 53.016 | 5.702 | 7.36 | 10.66 | Current
trunk:AV1:A2:audio:1 | 9 | 44.175 | 5.702 | 7.36 | 8.841 | Current
trunk:AV1:A2:audio:1 | 10 | 44.175 | 7.04 | 7.36 | 1.338 | Current
trunk:AV1:A2:audio:1 | 11 | 43.535 | 7.04 | 7.36 | 0.64 | Current
trunk:AV1:A2:audio:1 | 12 | 43.455 | 6.9504 | 7.36 | 0.12011 | Current
trunk:AV1:A2:audio:1 | 13 | 40.575 | 9.27 | 7.36 | 3.698 | Current
trunk:AV1:A2:audio:1 | 14 | 37.695 | 6.9504 | 7.36 | 3.698 | Current
trunk:AV1:A2:audio:1 | 15 | 37.615 | 7.04 | 7.36 | 0.12011 | Current
trunk:AV1:A2:audio:1 | 16 | 36.975 | 7.04 | 7.36 | 0.64 | Current
trunk:AV1:A2:audio:1 | 17 | 36.975 | 5.702 | 7.36 | 1.338 | Current
trunk:AV1:A2:audio:1 | 18 | 13.53 | 5.702 | 7.36 | 23.445 | Current
drop:AV1:A2:audio:1:S281 | 1 | 13.53 | 5.702 | 7.36 | 0 | Current
drop:AV1:A2:audio:1:S281 | 2 | 13.53 | 7.04 | 7.36 | 1.338 | Current
drop:AV1:A2:audio:1:S281 | 3 | 12.225 | 7.04 | 7.36 | 1.305 | Current
drop:AV1:A2:audio:1:S281 | 4 | 12.225 | 6.9326 | 7.4384 | 0.13301 | Current
drop:AV1:A2:audio:1:S281 | 5 | 12.225 | 6.6187 | 8.85 | 1.4461 | Current
drop:AV1:A2:audio:1:S281 | 6 | 12.225 | 3.9 | 8.85 | 2.7187 | Current
drop:AV1:A2:audio:1:S282 | 1 | 27.03 | 5.702 | 7.36 | 0 | Current
drop:AV1:A2:audio:1:S282 | 2 | 27.03 | 7.04 | 7.36 | 1.338 | Current
drop:AV1:A2:audio:1:S282 | 3 | 25.725 | 7.04 | 7.36 | 1.305 | Current
drop:AV1:A2:audio:1:S282 | 4 | 25.725 | 6.9326 | 7.4384 | 0.13301 | Current
drop:AV1:A2:audio:1:S282 | 5 | 25.725 | 6.6187 | 8.85 | 1.4461 | Current
drop:AV1:A2:audio:1:S282 | 6 | 25.725 | 3.9 | 8.85 | 2.7187 | Current
trunk:AV1:A3:audio:-1 | 1 | 49.275 | 0.95 | 1.4 | 0 | Current
trunk:AV1:A3:audio:-1 | 2 | 48.735 | 0.95 | 1.4 | 0.54 | Current
trunk:AV1:A3:audio:-1 | 3 | 48.735 | 0.95 | -2.24 | 3.64 | Current
trunk:AV1:A3:audio:-1 | 4 | 48.735 | 4.33 | -2.24 | 3.38 | Current
trunk:AV1:A3:audio:-1 | 5 | 48.735 | 4.33 | -3.3 | 1.06 | Current
trunk:AV1:A3:audio:-1 | 6 | 53.016 | 4.33 | -3.3 | 4.281 | Current
trunk:AV1:A3:audio:-1 | 7 | 53.016 | 5.71 | -3.3 | 1.38 | Current
trunk:AV1:A3:audio:-1 | 8 | 53.016 | 5.71 | -7.36 | 4.06 | Current
trunk:AV1:A3:audio:-1 | 9 | 44.175 | 5.71 | -7.36 | 8.841 | Current
trunk:AV1:A3:audio:-1 | 10 | 44.175 | 7.04 | -7.36 | 1.33 | Current
trunk:AV1:A3:audio:-1 | 11 | 43.535 | 7.04 | -7.36 | 0.64 | Current
trunk:AV1:A3:audio:-1 | 12 | 43.455 | 6.9504 | -7.36 | 0.12011 | Current
trunk:AV1:A3:audio:-1 | 13 | 40.575 | 9.27 | -7.36 | 3.698 | Current
trunk:AV1:A3:audio:-1 | 14 | 37.695 | 6.9504 | -7.36 | 3.698 | Current
trunk:AV1:A3:audio:-1 | 15 | 37.615 | 7.04 | -7.36 | 0.12011 | Current
trunk:AV1:A3:audio:-1 | 16 | 36.975 | 7.04 | -7.36 | 0.64 | Current
trunk:AV1:A3:audio:-1 | 17 | 36.975 | 5.71 | -7.36 | 1.33 | Current
trunk:AV1:A3:audio:-1 | 18 | 5.475 | 5.71 | -7.36 | 31.5 | Current
trunk:AV1:A3:audio:-1 | 19 | 2.35 | 5.71 | -7.36 | 3.125 | Current
drop:AV1:A3:audio:-1:S283 | 1 | 2.35 | 5.71 | -7.36 | 0 | Current
drop:AV1:A3:audio:-1:S283 | 2 | 2.35 | 7.65 | -7.36 | 1.94 | Current
drop:AV1:A3:audio:-1:S283 | 3 | 2.35 | 7.65 | -7.703 | 0.343 | Current
drop:AV1:A3:audio:-1:S283 | 4 | 0 | 7.65 | -7.703 | 2.35 | Current
drop:AV1:A3:audio:-1:S283 | 5 | 0 | 7.65 | -7.943 | 0.24 | Current
drop:AV1:A3:audio:-1:S283 | 6 | 0 | 6.2 | -7.943 | 1.45 | Current
drop:AV1:A3:audio:-1:S283 | 7 | 0 | 6.2 | -8.3 | 0.357 | Current
drop:AV1:A3:audio:-1:S283 | 8 | -0.14 | 6.2 | -8.3 | 0.14 | Current
drop:AV1:A3:audio:-1:S284 | 1 | 2.35 | 5.71 | -7.36 | 0 | Current
drop:AV1:A3:audio:-1:S284 | 2 | 2.35 | 7.65 | -7.36 | 1.94 | Current
drop:AV1:A3:audio:-1:S284 | 3 | 2.35 | 7.65 | -7.703 | 0.343 | Current
drop:AV1:A3:audio:-1:S284 | 4 | 0 | 7.65 | -7.703 | 2.35 | Current
drop:AV1:A3:audio:-1:S284 | 5 | 0 | 7.65 | -12.363 | 4.66 | Current
drop:AV1:A3:audio:-1:S284 | 6 | 0 | 6.2 | -12.363 | 1.45 | Current
drop:AV1:A3:audio:-1:S284 | 7 | 0 | 6.2 | -11.9 | 0.463 | Current
drop:AV1:A3:audio:-1:S284 | 8 | -0.14 | 6.2 | -11.9 | 0.14 | Current
drop:AV1:A3:audio:-1:S285 | 1 | 18.975 | 5.71 | -7.36 | 0 | Current
drop:AV1:A3:audio:-1:S285 | 2 | 18.975 | 7.04 | -7.36 | 1.33 | Current
drop:AV1:A3:audio:-1:S285 | 3 | 18.975 | 6.9326 | -7.4383 | 0.13293 | Current
drop:AV1:A3:audio:-1:S285 | 4 | 18.975 | 6.2709 | -10.414 | 3.0484 | Current
drop:AV1:A3:audio:-1:S285 | 5 | 18.975 | 5.6 | -10.414 | 0.67086 | Current
drop:AV1:A3:audio:-1:S285 | 6 | 18.975 | 5.6 | -10.75 | 0.336 | Current
drop:AV1:A3:audio:-1:S286 | 1 | 32.475 | 5.71 | -7.36 | 0 | Current
drop:AV1:A3:audio:-1:S286 | 2 | 32.475 | 7.04 | -7.36 | 1.33 | Current
drop:AV1:A3:audio:-1:S286 | 3 | 32.475 | 6.9326 | -7.4383 | 0.13293 | Current
drop:AV1:A3:audio:-1:S286 | 4 | 32.475 | 6.2709 | -10.414 | 3.0484 | Current
drop:AV1:A3:audio:-1:S286 | 5 | 32.475 | 5.6 | -10.414 | 0.67086 | Current
drop:AV1:A3:audio:-1:S286 | 6 | 32.475 | 5.6 | -10.75 | 0.336 | Current
trunk:AV1:A3:audio:1 | 1 | 49.275 | 0.95 | 1.4 | 0 | Current
trunk:AV1:A3:audio:1 | 2 | 48.735 | 0.95 | 1.4 | 0.54 | Current
trunk:AV1:A3:audio:1 | 3 | 48.735 | 0.95 | -2.24 | 3.64 | Current
trunk:AV1:A3:audio:1 | 4 | 48.735 | 4.33 | -2.24 | 3.38 | Current
trunk:AV1:A3:audio:1 | 5 | 48.735 | 4.33 | -3.3 | 1.06 | Current
trunk:AV1:A3:audio:1 | 6 | 53.016 | 4.33 | -3.3 | 4.281 | Current
trunk:AV1:A3:audio:1 | 7 | 53.016 | 5.71 | -3.3 | 1.38 | Current
trunk:AV1:A3:audio:1 | 8 | 53.016 | 5.71 | 7.36 | 10.66 | Current
trunk:AV1:A3:audio:1 | 9 | 44.175 | 5.71 | 7.36 | 8.841 | Current
trunk:AV1:A3:audio:1 | 10 | 44.175 | 7.04 | 7.36 | 1.33 | Current
trunk:AV1:A3:audio:1 | 11 | 43.535 | 7.04 | 7.36 | 0.64 | Current
trunk:AV1:A3:audio:1 | 12 | 43.455 | 6.9504 | 7.36 | 0.12011 | Current
trunk:AV1:A3:audio:1 | 13 | 40.575 | 9.27 | 7.36 | 3.698 | Current
trunk:AV1:A3:audio:1 | 14 | 37.695 | 6.9504 | 7.36 | 3.698 | Current
trunk:AV1:A3:audio:1 | 15 | 37.615 | 7.04 | 7.36 | 0.12011 | Current
trunk:AV1:A3:audio:1 | 16 | 36.975 | 7.04 | 7.36 | 0.64 | Current
trunk:AV1:A3:audio:1 | 17 | 36.975 | 5.71 | 7.36 | 1.33 | Current
trunk:AV1:A3:audio:1 | 18 | 5.475 | 5.71 | 7.36 | 31.5 | Current
trunk:AV1:A3:audio:1 | 19 | 2.35 | 5.71 | 7.36 | 3.125 | Current
drop:AV1:A3:audio:1:S287 | 1 | 2.35 | 5.71 | 7.36 | 0 | Current
drop:AV1:A3:audio:1:S287 | 2 | 2.35 | 7.65 | 7.36 | 1.94 | Current
drop:AV1:A3:audio:1:S287 | 3 | 2.35 | 7.65 | 7.703 | 0.343 | Current
drop:AV1:A3:audio:1:S287 | 4 | 0 | 7.65 | 7.703 | 2.35 | Current
drop:AV1:A3:audio:1:S287 | 5 | 0 | 7.65 | 7.943 | 0.24 | Current
drop:AV1:A3:audio:1:S287 | 6 | 0 | 6.2 | 7.943 | 1.45 | Current
drop:AV1:A3:audio:1:S287 | 7 | 0 | 6.2 | 8.3 | 0.357 | Current
drop:AV1:A3:audio:1:S287 | 8 | -0.14 | 6.2 | 8.3 | 0.14 | Current
drop:AV1:A3:audio:1:S288 | 1 | 2.35 | 5.71 | 7.36 | 0 | Current
drop:AV1:A3:audio:1:S288 | 2 | 2.35 | 7.65 | 7.36 | 1.94 | Current
drop:AV1:A3:audio:1:S288 | 3 | 2.35 | 7.65 | 7.703 | 0.343 | Current
drop:AV1:A3:audio:1:S288 | 4 | 0 | 7.65 | 7.703 | 2.35 | Current
drop:AV1:A3:audio:1:S288 | 5 | 0 | 7.65 | 12.363 | 4.66 | Current
drop:AV1:A3:audio:1:S288 | 6 | 0 | 6.2 | 12.363 | 1.45 | Current
drop:AV1:A3:audio:1:S288 | 7 | 0 | 6.2 | 11.9 | 0.463 | Current
drop:AV1:A3:audio:1:S288 | 8 | -0.14 | 6.2 | 11.9 | 0.14 | Current
drop:AV1:A3:audio:1:S289 | 1 | 18.975 | 5.71 | 7.36 | 0 | Current
drop:AV1:A3:audio:1:S289 | 2 | 18.975 | 7.04 | 7.36 | 1.33 | Current
drop:AV1:A3:audio:1:S289 | 3 | 18.975 | 6.9326 | 7.4383 | 0.13293 | Current
drop:AV1:A3:audio:1:S289 | 4 | 18.975 | 6.2709 | 10.414 | 3.0484 | Current
drop:AV1:A3:audio:1:S289 | 5 | 18.975 | 5.6 | 10.414 | 0.67086 | Current
drop:AV1:A3:audio:1:S289 | 6 | 18.975 | 5.6 | 10.75 | 0.336 | Current
drop:AV1:A3:audio:1:S290 | 1 | 32.475 | 5.71 | 7.36 | 0 | Current
drop:AV1:A3:audio:1:S290 | 2 | 32.475 | 7.04 | 7.36 | 1.33 | Current
drop:AV1:A3:audio:1:S290 | 3 | 32.475 | 6.9326 | 7.4383 | 0.13293 | Current
drop:AV1:A3:audio:1:S290 | 4 | 32.475 | 6.2709 | 10.414 | 3.0484 | Current
drop:AV1:A3:audio:1:S290 | 5 | 32.475 | 5.6 | 10.414 | 0.67086 | Current
drop:AV1:A3:audio:1:S290 | 6 | 32.475 | 5.6 | 10.75 | 0.336 | Current
trunk:AV1:MIC:mic:-1 | 1 | 49.275 | 0.95 | 1.4 | 0 | Current
trunk:AV1:MIC:mic:-1 | 2 | 49.275 | 0.03 | 1.4 | 0.92 | Current
trunk:AV1:MIC:mic:-1 | 3 | 49.275 | 0.03 | -1.4 | 2.8 | Current
trunk:AV1:MIC:mic:-1 | 4 | 41.08 | 0.03 | -1.4 | 8.195 | Current
drop:AV1:MIC:mic:-1:S291 | 1 | 41.08 | 0.03 | -1.4 | 0 | Current
drop:AV1:MIC:mic:-1:S291 | 2 | 41.08 | 0.03 | -2.62 | 1.22 | Current
drop:AV1:MIC:mic:-1:S291 | 3 | 41.3 | 0.03 | -2.62 | 0.22 | Current
drop:AV1:MIC:mic:-1:S291 | 4 | 41.3 | 1.81 | -2.62 | 1.78 | Current
drop:AV1:MIC:mic:-1:S291 | 5 | 41.08 | 1.7654 | -2.62 | 0.22447 | Current
drop:AV1:MIC:mic:-1:S291 | 6 | 41.08 | 1.9 | -2.62 | 0.1346 | Current
trunk:AV1:MIC:mic:1 | 1 | 49.275 | 0.95 | 1.4 | 0 | Current
trunk:AV1:MIC:mic:1 | 2 | 49.275 | 0.03 | 1.4 | 0.92 | Current
trunk:AV1:MIC:mic:1 | 3 | 44.45 | 0.03 | 1.4 | 4.825 | Current
drop:AV1:MIC:mic:1:S292 | 1 | 44.45 | 0.03 | 1.4 | 0 | Current
drop:AV1:MIC:mic:1:S292 | 2 | 44.45 | 0.03 | 0.45 | 0.95 | Current
drop:AV1:MIC:mic:1:S292 | 3 | 44.45 | 1.88 | 0.45 | 1.85 | Current
drop:AV1:A1:audio:-1:S275 | 1 | 38.94 | 7.9532 | -7.36 | 0 | Retired
drop:AV1:A1:audio:-1:S275 | 2 | 38.94 | 7.9532 | -11.6 | 4.24 | Retired
drop:AV1:A1:audio:-1:S275 | 3 | 38.94 | 3 | -11.6 | 4.9532 | Retired
drop:AV1:A1:audio:1:S277 | 1 | 38.94 | 7.9532 | 7.36 | 0 | Retired
drop:AV1:A1:audio:1:S277 | 2 | 38.94 | 7.9532 | 11.6 | 4.24 | Retired
drop:AV1:A1:audio:1:S277 | 3 | 38.94 | 3 | 11.6 | 4.9532 | Retired